## Slide 1
Process Change Request
Flow Process Draft
Background
PCR Before After Summary
Proposed Flow Process
Timeline
Important Concerns
0
Notes: Background :
1) History Long L.T of FR6F Approval
2) Related to Process Change Business Process and Procedure belong to PE
3) Control and Monitoring regarding fulfillment PCR requirement coordinated by PE and supported by QC

## Slide 2
1. Background
Change business flow from Internal Niterra Indonesia to Customer OEM/OES
PE
Sales OE
Procurement
Quality
Customers
PE
Procurement
Quality
Current Condition
Proposed Condition
Passthrough PCR
KD Parts PCR
KD Parts PCR
Internal PCR
Internal PCR
Internal Review
Current Condition : Passthrough & Customer PCR activity lead by Sales OE
Proposed Condition : Passthrough & Customer PCR activity lead by PE, Internal Review : Localization & Customer Approval Need review lead by PE. For Localization Request will submit to GHQ by PE or Sales Marketing.
Passthrough PCR
Customers
Local Supplier PCR
Local Supplier PCR

## Slide 3
Step |  | Before | After | Remark
Input | Item | External : K/D, Passthrough, Supplier Internal : Niterra INA | External : K/D, Passthrough, Supplier Internal : Niterra INA | Originator Dept are department where item of changes are initially triggered.
 | Change Point | No Localization Stage | Must Pass Localization Stage | 
Process | Item | Sales, PE, Quality As Window Dept PE & Sales control & monitoring PCR Event | 1) PE as Window Dept 2) PE control & monitoring PCR event 3) QA Support internal documents update | Internal activity controlled by PE
 | Change Point | Passthrough by Sales, Inhouse by PE | PE as Dept window for Overseas communication & PCR event (sales OE acknowledge) | 
Output | Item | 1) PCR Customer Submission, Feedback & Judgement by Sales OE | 1) PCR Customer Submission, Feedback & Judgement by PE (sales OE acknowledge) 2) PCR Internal Approval | Control & Monitoring by PE
 | Change Point | Sales as Dept window for PCR Submission until PCR Judgement | PE as Dept window for PCR Submission until PCR Judgement (sales OE acknowledge) | 
2. PCR Before After Summary
Notes: Background  ada di deskripsi page 1
Before – After simple statement (change point)
 Context Coordination & Fulfillment : Before ( Internal Process by PE, External Process By Sales ), After ( Internal & External Process by PE )
3) Tabel Follow Page 3  Dengan panel review ( PE + DGM + GM ) judgment Lokalisasi di awal sebelum process PCR
4) Job load & countermeasure (if not enough)
 Cross check Current Job Load, Cross Check & Simulate with additional PCR Job ( Our current PCR Job + Customer PCR Job in each flow )

## Slide 4
Overseas PCR Proposed
KD Parts
Passthrough Parts
Received by PM or GM MKT
Received by Niterra Dept
Internal Proposed :
From Niterra Indonesia
Supplier
PIC Localization Sheet : Related Manufacturing : PE
Related to Business Administration : Sales Marketing
Localization Panel
Localization Sheet
Customer Submit
Proposed Localization
Localization Judgement
STOP
Internal Requirement List
Internal QM Verification
Mass Production
1st Delivery
Submit PCR to Customer
Customer Feedback & Requirement
Trial & Evaluation
Customer Judgement
Trial & Evaluation
OK
NG
Need
No Need
OK
NG
No Need
Need
3. Proposed Flow Process
Intenral QM Verification
OK
OK
NG
PE Window
Internal Requirement List

## Slide 5
No | Item | Lead by | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | Remark
 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 
1 | Revise PCR Procedure : Localization Sheet, KD Parts, External, & Passthrough Parts | PE |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | PCR Procedure Finish : Flow Process, PIC, Scope of Work & Authority | PE |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Sharing Knowledge & Training ( Customer BP ): Flow , Communication, Customer PIC : 2W : AHM, YIMM, SIM, KMI 4W : ADM, HPM, SIM, TAM | Sales OE |  |  |  |  |  |  |  |  |  |  |  |  | Introduction Sharing knowledge
4 | Training Passthrough Part : Spark Plug, Sensor Oxygen, Sensor LAF, Sensor Knock | PE |  |  |  |  |  |  |  |  |  |  |  |  | Refer to Training Schedule
5 | Hand Over Transition Phase | Sales OE |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | PE fully lead PCR | PE |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | PCR Control Improvement ( Spreadsheet to Portal application ) | PE |  |  |  |  |  |  |  |  |  |  |  |  | Refer to IT Project
8 | PCR Output to Material ( BOM Master Application ) | PE |  |  |  |  |  |  |  |  |  |  |  |  | Refer to IT Project
4.Timeline
Rome was not built in a day
Notes: 1 ) July start Job Transfer PCR from Sales.
2) Customer BP, refer to Quality Manual.
3) Paralel untuk perkenalan ke customer 1 hari satu customer ( face to face ), dengan preliminari lewat email

## Slide 6
5. Important Concerns
No | Concern/Important Item | Remark
1 | Sales OE will join when PCR meeting with Customer, PE only explain for technical meeting not for business required | -
2 | Due to PCR have limited time, we need to prevent the PCR delay | PCR Panel Review
3 | How to utilize the working ratio in Sales OE when PCR transfer to PE? | -
4 | Current PCR Obstacles Some Overseas (e.g Niterra North America) : too slow respon Niterra Japan : Take Time required documents & lack of PCR information/materials Niterra Indonesia : Lack of monitoring | PCR Panel Review
5 | To monitoring PCR (Supplier/KD Parts → Internal/Oversease → PE → Customer) will use Monitoring Portal like Purchase Request (similar features) | October 2025
6 | Transfer Business Process from Sales OE to PE need to revise : Business Process Procedure Working Instructions | July 2025
7 | PCR Task Transfer transition in June-July and will lead by PE by July | Introduction to Customer, etc and start Lead by PE on July
8 | IE Workload Analysis (additional PCR transfer from Sales OEM to IE) | End of June 2025
9 | Socialization new PCR Procedure to all related Dept | -

## Slide 7
Appendix

## Slide 8
PCR Matrix
Based on 3 classification :
Internal Proposal basically follow originator timeline, but better submit when the originator have a plan to change
For External Proposal (OEM Customer) it will take time atleast 8 months but can be advance when we prepared the customer requirements before we submit the proposal
For Localization request that need new material or equipment, it will takes time around 16 months, but if no need order new material or equipment it will take around 12 months
Red Circle : Need Customer Approval
Green Circle : No Need Customer Approval
Change Classification Lead Time
Appendix 2 Classification
Notes: 1) Tambah keterangan M = moonth

## Slide 9
Sample Case (That PE Know) :
1. Honda 4W - Sensor Oxygen : New Glass Tube Application
2. SIM 4W - Sensor Knock : Change Source from Japan to Wells Vehicle
3. Honda 2W - Sensor Oxygen : Change dimension
4. etc
Sample Case (That PE Know) :
1. AHM - Spark Plug : Additional Source, Production Change (Plating, Welding Tip Process)
2. AHM - Sensor Oxygen : Production Site Change
Passthrough Part Model 1
Passthrough Part Model 2
Passthrough Part Model 3
Sample Case (That PE Know) :
1. SIM 4W - Sensor Knock : Company Name Change from Wells Vehicle to Niterra North America
Appendix 3. Current Detail Process Pass Thru
Notes: 1) Cross check sekali lagi terkait current existing

## Slide 10
Appendix 4. Flow Process PCR Proposed
Definition of Proposer
Department that conduct the change